## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a System Architect, I want to research Twilio webhook execution flows so that I can map out secure multi-level IVR routing schemas. | Must Have | Planning | Backend Team | Completed
Sprint 2 | Sprint 2 | US002 | As a backend engineer, I want to configure a FastAPI webhook to receive Twilio payloads and handle Speech-to-Text (STT) | Must Have | Twilio Number | Dev Team | Completed
Sprint 2 | Sprint 2 | US003 | As a DevOps Engineer, I want to deploy the FastAPI server using a secure public URL (ngrok) to establish real-time communication with Twilio webhooks. | Should Have | Core API | Dev Team | Completed
Sprint 3 | Sprint 3 | US004 | As a Backend Developer, I want to implement session management (CallSid) and Polly SSML to enable a natural conversational hospital IVR experience. | Should Have | STT Setup | Backend Team | Completed
Sprint 3 | Sprint 3 | US005 | As a Voice Developer, I want to integrate Twilio's Speech Recognition (Gather) and regex NLU to process patient delivery intents efficiently. | Must Have | DTMF Baseline | Backend Team | Completed
Sprint 4 | Sprint 4 | US006 | As a Backend Developer, I want to configure Twilio SMS APIs and secure SMTP logic so that diagnostic reports are sent reliably to patients. | Must Have | API Config | Backend Team | Ongoing
Sprint 4 | Sprint 4 | US007 | As a QA Engineer, I want to execute full system regression testing covering low-confidence loops and DTMF fallbacks to ensure an error-free flow. | Should Have | Integration | Backend Team | Ongoing

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Analyze Twilio TwiML constraints; map out the /handle-delivery-options multi-turn prompt strategy. | 2026-02-13 | 2026-02-16 | Documentation | Research | Done | 8 | bar: Day 1 to Day 4
US002 | T2 | Developed the foundational API endpoints required to operate the traditional IVR system. | 2026-02-27 | 2026-03-02 | Backend 1 | Model Training | Done | 8 | bar: Day 4 to Day 7
US003 | T3 | Construct the /voice webhook to catch Twilio requests and map numeric Patient IDs natively. | 2026-02-27 | 2026-03-02 | Backend 2 | API Dev | Done | 8 | bar: Day 5 to Day 8
US004 | T4 | Incorporated Speech-to-Text (STT) and Natural Language Understanding (NLU) to accurately detect and interpret caller intent. | 2026-03-13 | 2026-03-16 | Backend 3 | TTS Dev | Done | 8 | bar: Day 8 to Day 11
US005 | T5 | Implementing a system to send sms or mail to patients preffered place | 2026-03-15 | 2026-03-16 | Backend 4 | API Dev | Done | 8 | bar: Day 11 to Day 12
US006 | T6 | Write the code to send SMS via Twilio API and send Emails using Gmail SMTP. | 2026-03-27 | 2026-03-30 | Backend 1 | API Dev | Done | 8 | bar: Day 13 to Day 16
US007 | T7 | Test what happens if the caller says nothing or Twilio misunderstands them. | 2026-03-28 | 2026-03-30 | Frontend 1 | QA / Test | Done | 6 | bar: Day 17 to Day 19

## Stand Up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Unable to find clear reference documentation on planning secure webhook flows locally. | Researched and utilized ngrok documentation to map out the FastAPI server architecture securely.
Sprint 2 | Day 4 | Ngrok tunnel session expired repeatedly, causing Twilio webhook 502 errors during dev. | Configured a static Ngrok domain for a stable development connection.
Sprint 2 | Day 5 | Delay in Twilio gathering inputs, causing the IVR to miss immediate button presses. | Updated TwiML <Gather> timeout and handled raw digits explicitly in the FastAPI backend.
Sprint 3 | Day 8 | Speech-to-Text failing to accurately transcribe user speech over ambient background noise. | Added "Speech Model" hints to the Twilio <Gather> tag for better natural language accuracy.
Sprint 3 | Day 11 | Amazon Polly SSML tags crashing when parsing dynamic strings with special characters. | Implemented string sanitization before sending text variables to the <speak> SSML block.
Sprint 4 | Day 13 | SMS dispatch via Twilio failing during integration testing for unverified phone numbers. | Registered QA testing numbers in the Twilio console to authorize the messaging service.
Sprint 4 | Day 17 | End-to-end testing revealed calls dropping abruptly when the user stays completely silent. | Added a timeout fallback loop in the TwiML flow to gracefully reprompt the caller.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-02-13 | 2026-02-16 | Muddasani Nikhil | Read API docs before coding. | Guessing how Twilio routing works. | Documenting endpoints thoroughly. | Standardize webhook diagram.
2 | 2 | 2026-02-27 | 2026-03-02 | Muddasani Nikhil | Setting up a scalable backend architecture for webhook handlers | Jumping into coding without establishing a base folder structure | Building and documenting the backend webhook foundation | Established the foundational FastAPI backend architecture and environment variables
3 | 2 | 2026-02-27 | 2026-03-02 | Muddasani Nikhil | Adding strict request and response validation for SpeechResult payloads | Skipping input validation on existing API endpoints | REST API and TwiML development and code reviews | Implemented dual-input accessibility supporting both Speech and DTMF
4 | 3 | 2026-03-13 | 2026-03-16 | Muddasani Nikhil | Using reusable TwiML generation functions to speed up development | Duplicating response building logic across different webhooks | Iterative call flow improvements based on caller feedback | Standardized voice configuration utilizing the Polly.Aditi voice model
5 | 3 | 2026-03-15 | 2026-03-16 | Muddasani Nikhil | Testing speech recognition and intent matching modules in isolation | Merging conversational modules without unit-level verification | Stress testing and security hardening across all telecom modules | Added localized conversational prompts and timeout handling for en-IN
6 | 4 | 2026-03-27 | 2026-03-30 | Muddasani Nikhil | Implementing centralized persistent session management from the start | Relying on a stateless or highly volatile in-memory dictionary | Call session state tracking and health monitoring | Configured initial call tracking utilizing the Twilio CallSid
7 | 4 | 2026-03-28 | 2026-03-30 | Muddasani Nikhil | Running regression tests on call flows after updating state management | Migrating all state logic without incremental testing checkpoints | Testing call session management workflows post-migration | Created nested multi-level IVR sub-menus for lab results & Diagonisis